## Pictures Traffic lights
Phase
Illumination | Case or not | Green | Yellow | Red | Red&Yellow
Weak | Witout case
With case
Medium | Witout case
With case
Strong | Witout case
With case

## SCRUM
Provisorial Backlog (practice) | [5 empty] | Provisorial Backlog (theory )
Nr. | Tasks that are in general necessray to reach the "final goal" ("final goal" = autonomously driving truck taht stops if the traffic light shines red and continue otherwise) | Goal description | Planned time units | Used time units | Done? [Yes] / [No] | Nr. | Creation of material for other students | Goal description | Needed time units | Used time units | Done? [Yes] / [No]
1 | decide about "final traffic light model" (build/bought) | It is decided which type of traffic light should be used in condition to be able to create the data set. | 1 | 1 | Yes | 1 | Theoretical exercices | Theoretical exercises for the students of the next semester are created. | 6
2 | find and implement a labeling software for data set | Information about labeling softwares collected. Based ond the infomation was a labelingsoftware for the data set chosen and instaled. | 4 | 12 | Yes | 2 | Practical task description | Task descriptions for the lab project for the students is finnished. | 6
3 | take pictures for first data set | Pictures of the chosen traffic light with the truck webcam are taken and stored. | 6 | 5 | Yes | 3 | Videos | Teaching videos in which the learning content get presented is created. | 25
4 | research and create a repoistory (database) with github. The database is needed for the dataset which will get used. | Information about the github as a repository (database) is collected. The repository is according to the found information created. | 5 | 7 | Yes | 4 | Presentation (powerpoint) | The powerpoint presentation with the content that will be shared with the other students was created. Additionaly, a presenatiation for the final presenatation is done. | 20
5 | data augmentation | More pictures are for the data set taken and argumented. | 3 |  |  | 5 | Collection of (research) results | A collection with all research results of this semester is completed. | 50?
6 | Label the pictures for the dataset | Label the pictures for the dataset. | 4 | 7 | Yes | 6 | Handout for the other students with texts and descriptions | A handout with the teaching content for the students was created. | 20
7 | create a first small data set | Information about the data set creation are sellected. The dataset was with the first taken pictures created. | 3 | 7 | Yes |  | define learning goals
8 | create the training data set | Training data set is created. | 1 | 0.1 | Yes |  |  | Design a lab experimentguidelineforthestudentsofthenextsemester. The studentsshouldbebusyfor2 ECTS (60). Includelearninggoals. Youcanuseyourpracticalexperiencewiththelab problemandaskthenextsemestertobuildon it(i.e. improvedata, improveCNN accuracy).
9 | create validation data set | Validation data set is created. | 1 | 0.1 | Yes |  |  | Design onetotwotheorylecturestofillthegapbetweengeneraltheoryandourlab setting(Pi, TPU, Data, etc). Inculdelearninggoals. A lecturetypicallynot onlyincludesa presentation, but also littlequizzesandtasksforthestudentstosolveafter a block ofinformationtounderstandandanchorthenewinfo(similartotheOpenHPIcourse). Sincewearein timesofCorona, recordyourlectures(studio& recordingSW will beprovided) anduploadittogetherwiththeproblemsin a Relax lecture(guidancewill beprovided).
10 | research how to implement the dataset to the CNN. | It is through research known, how to connect the dataset with the CNN. | 8
11 | Create environment for CNN (i.e. connection/link to repository) | The environment for the CNN is set up and programmed. | 20
12 | General research about CNN with TPU. Research about the CNN structure with the TPU | General information about the CNN with TPU (what is needed, pros, cons,…) are known. Furthermore are information about the CNN structures at the TPU collected and we are able to programm a CNN that is with the TPU working. | 60 - 80
13 | create a layer structure for CNN | A layer structure is for the CNN created. The CNN contains approximately 100 -120 layers. | 30
14 | choose and test activation functions | Activation functions according our CNN are chosen and the activation functions are tested. | 5
15 | set optimizers for CNN | The optimizers are in condtion to have a better valdiation/accuracy rate set. | 5 - 15
16 | figure out right hyper parameter for CNN | The hyper parameters are in condtion to have a better valdiation/accuracy rate set. | 5 - 15
17 | Train the CNN | The CNN is with the training data set trained. | 20 - 100
18 | Test CNN (colab) | The CNN is on colab with the validation data set tested to ist function. | 2 - 10
19 | Research how to save trained CNN | It is decided how and where to store the trained CNN. | 4
20 | Edit functional CNN for the usage of TPU | The functional CNN is adapted to the requirements of the TPU. | 20 -60
21 | TPU: Export, convert, compile CNN and create new file with the output | The CNN is exported, converted and compiled to the TPU. Furthermore, a new file with the output was created. | 20 - 60
22 | Transfere the finished CNN to the raspberry Pi and connect it with the hardware. | The finished CNN was to the raspberry Pi transferred and was with the hardware connected (camera connection and steering; integrate with the programm). | 10
23 | Test "new" CNN on the pi with the TPU and the hardware (truck) | The for theTPU adjusted CNN was tested on the pi through the hardware (truck). | 20
| Things that could be optimized | Detailed description | Goal description
1 | Data set optimization | Optimize the data set in order to get a higher accuracy. Take tehrefore more pictures and extend the dataset. | More pictures are taken, labeled and implemented to an dataset.
2 | Traffic light optimization | Take the at amazon bought "new" traffic light and implement the arduino to it. | The "new" traffic light is connected with the arduinoNano and can be used according the needs.
3 | find out how to adjust the resoultions of the pictures made by the webcam (pi, ELP-handout?) | Find out how to adjust the resolution problems of the pictures made by the webcam. Check therefore the settings at the pi and read maybe the ELP-manual.
4 | set the fps at the webcam | Set the fps at the webcam in condition to get pictures with a higher resoultion.
Nr. | Tasks that are in general necessray to reach the "final goal" ("final goal" = autonomously driving truck taht stops if the traffic light shines red and continue otherwise) | Goal description | Planned time units | Used time units | Done?
[Yes] / [No]
1 | decide about "final traffic light model" (build/bought) | It is decided which type of traffic light should be used in condition to be able to create the data set. | 1 | 1 | Yes
2 | find and implement a labeling software for data set | Information about labeling softwares collected. Based ond the infomation was a labelingsoftware for the data set chosen and instaled. | 4 | 12 | Yes
3 | take pictures for first data set | Pictures of the chosen traffic light with the truck webcam are taken and stored. | 6 | 5 | Yes
4 | research and create a repoistory (database) with github. The database is needed for the dataset which will get used. | Information about the github as a repository (database) is collected. The repository is according to the found information created. | 5 | 7 | Yes
5 | data augmentation | More pictures are for the data set taken and argumented. | 3
6 | Label the pictures for the dataset | Label the pictures for the dataset. | 4 | 7 | Yes
7 | create a first small data set | Information about the data set creation are sellected. The dataset was with the first taken pictures created. | 3 | 7 | Yes
8 | create the training data set | Training data set is created. | 1 | 0.1 | Yes
9 | create validation data set | Validation data set is created. | 1 | 0.1 | Yes
10 | research how to implement the dataset to the CNN. | It is through research known, how to connect the dataset with the CNN. | 8 | ? | Yes
11 | Create environment for CNN (i.e. connection/link to repository) | The environment for the CNN is set up and programmed. | 20 |  | Yes
12 | General research about CNN with TPU. Research about the CNN structure with the TPU | General information about the CNN with TPU (what is needed, pros, cons,…) are known. Furthermore are information about the CNN structures at the TPU collected and we are able to programm a CNN that is with the TPU working. | 60 - 80
Nr. | Tasks that are in general necessray to reach the "final goal" ("final goal" = autonomously driving truck taht stops if the traffic light shines red and continue otherwise) | Goal description | Planned time units | Used time units | Done?
[Yes] / [No]
13 | create a layer structure for CNN | A layer structure is for the CNN created. The CNN contains approximately 100 -120 layers. | 30 |  | Yes
14 | choose and test activation functions | Activation functions according our CNN are chosen and the activation functions are tested. | 5
15 | set optimizers for CNN | The optimizers are in condtion to have a better valdiation/accuracy rate set. | 5 - 15
16 | figure out right hyper parameter for CNN | The hyper parameters are in condtion to have a better valdiation/accuracy rate set. | 5 - 15
17 | Train the CNN | The CNN is with the training data set trained. | 20 - 100
18 | Test CNN (colab) | The CNN is on colab with the validation data set tested to ist function. | 2 - 10
19 | Research how to save trained CNN | It is decided how and where to store the trained CNN. | 4
20 | Edit functional CNN for the usage of TPU | The functional CNN is adapted to the requirements of the TPU. | 20 -60
21 | TPU: Export, convert, compile CNN and create new file with the output | The CNN is exported, converted and compiled to the TPU. Furthermore, a new file with the output was created. | 20 - 60
22 | Transfere the finished CNN to the raspberry Pi and connect it with the hardware. | The finished CNN was to the raspberry Pi transferred and was with the hardware connected (camera connection and steering; integrate with the programm). | 10
23 | Test "new" CNN on the pi with the TPU and the hardware (truck) | The for theTPU adjusted CNN was tested on the pi through the hardware (truck). | 20

## Lab tasks
Task | Goal description | Planned time [h]
Preparations to work | All necessary programs are installed, and accounts are set up. | 1
First truck connection | The connection between computer and truck (Raspberry Pi) is set up and works. | 0.5
Data set creation | A data set was created. Images are taken, labelled, augmented, and saved in the repository. | 10
Create a simple neural net | A simple neural net with xx layers was set up from scratch. The CNN can decide between cats and dogs / between different types of flowers / … | 10-15
Create a simple CNN | A simple CNN with xx layers was set up from scratch. The CNN can decide between cats and dogs / between different types of flowers / … | 10-15
Understanding of CNN for traffic light detection | The CNN that was for traffic light detection created is known and the working principle is understood. Furthermore, the connection between the CNN and GitHub is known and understood. | 1.5
Improve / complement the CNN | (incl. Adaption to TPU requirements & testing of TPU at the truck) | 20-25

## List of programs & accounts
Platform | Platform address | Account needed? | Download needed?
WinSCP | https://winscp.net/eng/download.php | No | Yes
VNC Viewer | https://www.realvnc.com/de/connect/download/viewer/ | No | Yes
putty | https://www.putty.org/ | No | Yes
Arduino IDE | https://www.arduino.cc/en/main/software | No | Yes
Anaconda prompt | https://www.anaconda.com/products/individual | No | Yes
Git | https://git-scm.com/downloads | Yes | Yes
GitHub | https://desktop.github.com/ | Yes | No
Google Colab | https://colab.research.google.com/notebooks/intro.ipynb | Yes | No
Platform | Platform address | Account needed? | Download needed?
WinSCP | https://winscp.net/eng/download.php | No | Yes
VNC Viewer | https://www.realvnc.com/de/connect/download/viewer/ | No | Yes
putty | https://www.putty.org/ | No | Yes
Arduino | https://www.arduino.cc/en/main/software | No | Yes
Anaconda prompt | https://www.anaconda.com/products/individual | No | Yes
Git | https://git-scm.com/downloads | No | Yes
GitHub | https://desktop.github.com/ | Yes | No
Google Colab | https://colab.research.google.com/notebooks/intro.ipynb | Yes | No

## GitHub comands
Comand | Description | Command Example
git clone | Copies and download an existing Git repository to your local computer. On the local computer made changes can be pushed directly to the repository. | git clone url
git config | Sets the author name and email address respectively to be used with your commits. | git config –-global user.name "name" git config –-global user.email "email address"
git init | Gets used to start a new repository. | git init repository name
git pull | takes and merges changes on the remote server to the working directory. | git pull repository link
git add | Adds files to the staging area. git add adds just a single file. git add * adds one or more files to the staging area. | git add file git add *
git commit | Records or snapshots the file permanently in the version history. Through the committed message is everybody able to know what the purpose of the file is. | git commit -m "message"
git status | Lists all files that have been committed. It shows if changes were successful. | git status
git log | Lists the version history of the current branch. Thus, it is too possible to see if the changes were successful. | git log
git push | Send the committed changes of the master branch to the remote repository. | git push variable name master
Comand | Description | Command Example
git clone | Copies and downloads an existing Git repository to your local computer. Changes made can locally be pushed directly to the repository. | git clone url
git config | Sets the authors name and email address. | git config –-global user.name "name"
git config –-global user.email "email address"
git init | Used to start a new repository. | git init repository name
Comand | Description | Command Example
git pull | Pulls changes from the remote server to the working directory. | git pull repository link
git add | Adds files to the staging area. | git add file
| git add: single file | git add *
git add *: one or more files
git commit | Records or snapshots the file permanently in the version history. The message informs about the purpose of the file. | git commit -m "message"
git status | Lists all files that have been committed. It shows if changes were successful. | git status
git log | Lists the version history of the current branch. It is possible to see if the changes were successful. | git log
git push | Sends the committed changes of the master branch to the remote repository. Attention: only push files with max. 100MB to GitHub. | git push variable name master

## Data set creation
Process step | Description
Image creation | Means to take images of the things that should be by the CNN identified, if possible, with the device that will be in the project used.
Labelling process | The things that should be identified will be marked and lettered with a special software.
Data augmentation | Means that existing images get changed just a little bit with the goal to create a bigger data set. Changes could be a changed picture section or the picture gets mirrored.
Creation of training and test data set | All data will get split into two groups. The one data group will be used just for training the CNN and the other group will be used to validate the accuracy of the CNN.
Integration of the dataset into a repository | The datasets get at one central space saved.
Process step | Description
Image creation | Take images of the things that should be identified by the CNN. If possible, use the same device as in the project.
Labelling process | Things that should be identified will be marked and lettered with a special software.
Data augmentation | Existing images are changed just a little bit to enarge the data set. Changes could be a different picture section or the picture is mirrored.
Creation of training and test data set | Data is split into two groups. One group will be used to train the CNN and the other group will be used to validate its accuracy.
Integration of the dataset into a repository | Data sets are saved in one central location.

## Install Labelimg
Step Nr. | Description
1 | Install Anaconda. Please use the following adress: https://www.anaconda.com/products/individual (skip the step if you already installed the system)
2 | Create a new environment in anaconda:
2.1 | Open the Anaconda Navigator
2.2 | Select “Environments”
2.3 | Select “Create”
2.4 | Name the new environment (i.e. “test”)
2.5 | Select at packages “python” (version 3.8)
2.6 | Push “create”
3 | Open anaconda prompt
4 | Change the file directory:
4.1 | To do this, write at (base) after the > symbol: activate test
4.2 | (test) is now activated
5 | Install labelimg by entering following function after the > symbol: pip install labelimg
6 | The software gets installed
7 | To use the program after installing write at the (test) environment after the > symbol: labelimg
Step Nr. | Description
1 | Install Anaconda. Please use the following adress: https://www.anaconda.com/products/individual
(skip the step if you already installed the system)
2 | Create a new environment in anaconda:
2.1 | Open the Anaconda Navigator
2.2 | Select “Environments”
2.3 | Select “Create”
2.4 | Name the new environment (i.e. “test”)
2.5 | Select at packages “python” (version 3.8)
2.6 | Push “create”
3 | Open anaconda prompt
4 | Change the file directory:
4.1 | To do this, write at (base) after the > symbol: activate test
4.2 | (test) is now activated
5 | Install labelimg by entering following function after the > symbol: pip install labelimg
6 | The software gets installed
7 | To use the program after installing write at the (test) environment after the > symbol: labelimg

## Time Marius
Date | Time (Marius) | Duration [h] (Marius) | Task (Marius) | Sum of duration Marius:
2020-04-26 | 13:00-17:00 | 4 | Research DeepPiCar | 158.75
2020-04-28 | 14:00-16:30 | 2.5 | Research DeepPiCar
| 16:45-20:00 | 3.25 | General research TensorFlow and Google Colab
2020-04-30 | 13:15-17:15 | 4 | Research TensorFlow models on TPU
2020-05-02 | 15:00-18:45 | 3.75 | Research requirements TPU
2020-05-05 | 12:30-18:15 | 5.75 | Analysing code snippets of DeepPiCar
2020-05-07 | 10:15 - 12:00 | 1.75 | meeting & discussion how to continue
2020-05-10 | 19:05-19:35 | 0.5 | Conference Call
2020-05-11 | 12:25-12:55 | 0.5 | Conference Call
2020-05-11 | 15:15-17:15 | 2 | Neuronal network graphics
2020-05-12 | 14:00 - 15:20, 21.30-02:10 | 7 | Neuronal network graphics, analysing code snippets, git: database
2020-05-13 | 11:30-13:30; 14:20-15:20 | 3 | Meeting, Neuronal network graphics
2020-05-25 | 19.30-21:00 | 1.5 | CNN Environment
2020-05-26 | 15:00-19:00 | 4 | Github, repository
2020-06-03 | 13:30-20:30 | 7 | Dataset, Import from Github, Tensor Flow Record
2020-06-04 | 10:00-10:30 | 0.5 | Meeting
2020-06-10 | 16:30-17:00; 17:30-18:30 | 1.5 | Conference Call, organising and structuring
2020-06-13 | 20:30-22:30 | 2 | Structuring the tasks/theorie/presentations
2020-06-15 | 19:15-2:00 | 6.75 | Searching and fixing errors in tfrecord data generation
2020-06-18 | 0:15 - 7:30 | 7.25 | Fixing new errors (tfrecords), trying to figure out how to train with the tfrecord dataset
2020-06-24 | 21:15-2:00 | 4.75 | Trying to solve usage of tfrecord files, research solution mnist dataset in tfrecord format
2020-06-25 | 08:00-10:00 | 2 | Meeting
2020-06-26 | 12:00-16:30 | 4.5 | Trying to solve usage of tfrecord files, "cleaning" some code sections
2020-06-27 | 14:00-20:15 | 6.25 | New CNN with fashion dataset using Github, without tfrecord
2020-06-29 | 12:30-13.45; 15:00-18:45; 19:00-20:00 | 6 | Usage of fashion dataset with tfrecord, List of sources and usefull information, Conference Call
2020-06-30 | 15:30-17:00; 22:00-05:45 | 9.25 | Conference Call, detailed code with fashion dataset (different models, saving the model, downloading files, unzipping csv dataset cleaning)
2020-07-01 | 15:00-19:00 | 4 | Adjusting theory and practical papers
2020-07-02 | 10:00-11:30; 13:00-17:00; 22:00-24:00 | 7.5 | Meeting, new CNN Dogs dataset
2020-07-03 | 22:00-2:30 | 4.5 | CNN Dog -> tfrecord...
2020-07-05 | 00:30-7:45; 16:00-17:45; 19:45-21:15 | 10.5 | CNN Dog -> dataset implementation, layerstructure, Conference Call, straighten out errors
2020-07-06 | 19:00-23:00 | 4 | Correct part of theory skript, conference call, commenting code
2020-07-07 | 16:15-22:00; 22:30-23:45 | 7 | Writing Chapter 7, commenting and cleaning the codes, conference call, presentation
2020-07-08 | 00:30-7:45; 15:00-23:30 | 15.75 | conference call, final comments on the codes, working on and finishing the presentation, correcting theory skript & lab skript & powerpoints
2020-07-09 | 0:30-4:45 | 4.25 | correcting/improving theory skript & lab skript & powerpoints, controlling the final material

## Time Anna
Date | Time (Anna) | Duration [h] (Anna) | Task (Anna) | Sum of durtaion Anna:
2020-04-26 | 09:00-11:30 | 2.5 | Search for literature about traffic lights | 189.75
2020-04-27 | 10:00 - 12:00; 14:00 - 18:00; 19:00 - 20:00 | 7 | read the articles about traffic lights
2020-04-28 | 15:30 - 18:00 | 2.5 | read the articles about traffic lights
2020-05-03 | 10:15 - 12:00; 17:15 - 18:30 | 3 | summarise the information from articles
2020-05-04 | 10:45 - 12:15, 14:00 - 15:30, 15:45 - 16:15 | 3.5 | Literature review, review bachelor thesis
2020-05-06 | 16:00 -18:45 | 2.75 | summarise the information from articles and work at text
2020-05-07 | 10:15 - 12:00; 14:45 - 17:00 | 4 | meeting & discussion how to continue; research for another traffic light
2020-05-10 | 11:00 - 12:15; 17:40 - 18:10; 19:05 - 19:35 | 2.25 | camera & raspberry pi research, reviewing all existing programm snippets
2020-05-11 | 10:40 - 11:50, 15:00 - 16:05; 12:25 - 12:55 | 2.75 | camera & raspberry pi research, find out how to set fps at camera
2020-05-12 | 17:00 - 18:45 | 1.75 | Data setcreation
2020-05-13 | 11:30 - 13:30; 21:00 - 21:00 | 3 | Settings webcam, model of traffic light
2020-05-17 | 17:50 -18:20 | 1.5 | documentation & installing programms
2020-05-20 | 13:30 - 18:30 | 5 | taking pictures for the dataset
2020-05-21 | 13:20 - 14:20 | 1 | Create product backlog
2020-05-25 | 11:00 - 12:00; 13:40 - 18:40; 20:20 - 23:20 | 9 | Image labeling
2020-05-26 | 11:40 - 12:40 | 1 | Documentation about lableimg
2020-05-27 | 13:30 - 17:30 | 4 | Lab meeting, product backlog
2020-05-28 | 10:00 - 10:55; 10:55 - 11:20 | 1.25 | Meeting, conference call
2020-05-30 | 16:20 - 17:35 | 1.25 | datset creation
2020-06-02 | 18:00 - 18:15 | 0.25 | conference call
2020-06-03 | 13:30 - 17:00; 19:20 - 21:50 | 6 | coplement the documentation
2020-06-04 | 08:40 - 11:10 | 2.5 | documentation, conference call
2020-06-08 | 11:00 - 12:00; 14:05 - 15:10 | 2 | documentation
2020-06-10 | 14:05 -16:05; 16:30 - 17:00 | 2.5 | documentation, conference call
2020-06-11 | 10:20 - 12:20; 15:30 - 16:20 | 2.75 | documentation, teaching material
2020-06-12 | 10:30 - 11:00; 17:15 - 18:15 | 1.5 | documentation, teaching material
2020-06-13 | 20:30 - 22:30 | 2 | Planning of delivering content (conference call)
2020-06-14 | 14:15 - 15:01; 16:15 - 17:15; 17:38 - 18:35 | 2.75 | documentation, teaching material
2020-06-15 | 16:00 - 18:00; 19:30 - 20:15 | 2.75 | documentation, teaching material
2020-06-16 | 18:42 - 20:44 | 2 | documentation, teaching material
2020-06-17 | 11:45 - 12:30; 14:06 - 15:06; 15:26 - 16:55; 18:03 - 19:10 | 4 | documentation, teaching material
2020-06-18 | 08:00 - 10:00 | 2 | conference call
2020-06-20 | 09:22 - 12:25 | 3 | documentation, teaching material
2020-06-21 | 11:00 - 12:30 | 1.5 | documentation, teaching material
2020-06-22 | 09:55 - 11:42; 13:42 - 16:00; 16:15 - 18:15; 18:35 - 19:20 | 6.75 | documentation, teaching material, citation / references
2020-06-23 | 11:15 - 12:15 | 1 | leraning goals, teaching material
2020-06-24 | 13:30 - 16:45 | 3.25 | leraning goals, teaching material
2020-06-25 | 08:40 - 11:45 | 3 | teaching material, conference call
2020-06-26 | 11:10 - 11:57; 14:00 - 15:00; 15:50 - 16:05 | 3 | teaching material
2020-06-27 | 11:00 - 12:30; 14:00 - 16:05 | 3.5 | Power point theory
2020-06-28 | 10:05 - 12:20; 15:05 -18:05; 19:25 - 21:25 | 6.25 | Power point theory, Power point Practice
2020-06-29 | 08:45 - 10:30; 10:45 - 12:15; 15:00 - 17:00; 19:00 - 20:00 | 6.25 | Presentations
2020-06-30 | 15:30 - 17:08; 19:10 - 20:25 | 3 | Presentations
01.07 | 11:26 - 12:26; 15:00 - 19:00 | 5 | teaching material
02.07 | 09:10 - 12:10; 14:40 - 16:55 | 3 | Conference call, teaching material
03.07 | 08:59 - 10:15; 13:10 - 13:55; 17:40 - 18:43; 19:28 -20:21 | 4 | teaching material
04.07 | 08:57 - 12:00; 14:00 - 18:45 | 7.75 | teaching material
05.07 | 10:00 - 10:45; 12:57 -16:00; 16:25 - 17:50; 18:50 - 20:56 | 7.25 | teaching material
06.07 | 10:45 - 12:02; 14:08 - 18:15; 20:00 - 23:35 | 8.75 | Final Presentation
07.07 | 11:00 - 12:25; 13:00 - 13:57; 15:20 - 22:03 | 9 | Teaching Material, presentation
08.07 | 11:15 - 11:55; 14:00 - 18:45; 19:20 - 22:28 | 8.5 | Teaching Material, presentation
09.07 | 08:00 - 12:00 | 4 | Final Presentation